## Blank
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.1.1 | Project Charter Revisions |  |  |  |  | 0%
1.2 | Research |  |  |  |  | 0%
1.3 | Projections |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Guidelines |  |  |  |  | 0%
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 0%
2.2 | Budget |  |  |  |  | 0%
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort and Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%

## Example
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE | Grønn programmering nettside
PROJECT MANAGER | Henrik Oppebøen
COMPANY NAME | Gruppe 17
DATE | 2025-02-06
TEAM MEDLEMMER | Henrik Oppebøen(HO), Filmon Yonas Gebrekristos(FYG),Fatima Manan Akhtar(FMA), Safia Zaid Argoub(SZA)
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Grønn programmering nettside
1.1 | Planlegging | HO,FYG,FMA,SZA | 2025-01-15 | 2025-01-22 | 7 | 100%
1.2 | Project Charter | HO,FYG,FMA,SZA | 2025-01-15 | 2025-01-22 | 7 | 100%
1.3 | Krav analyse | HO,FYG,FMA,SZA | 2025-01-15 | 2025-01-22 | 7 | 100%
1.3.1 | Bruker historier | HO,FYG,FMA,SZA | 2025-01-15 | 2025-01-22 | 7 | 100%
1.4 | Allokere team ressurser | HO,FYG,FMA,SZA | 2025-01-15 | 2025-01-22 | 7 | 100%
2.1 | Utførelse
2.2 | Lage prototype av nettside | HO,FYG,FMA,SZA | 2025-02-05 | 2025-03-28 | 51 | 10%
2.3 | Utvikle nettside med HTML | HO,FYG,FMA,SZA | 2025-03-08 | 2025-04-30 | 53 | 0%
3.1 | Testing
3.2 | Funksjonstesting |  |  |  |  | 0%
3.3 | Brukertesting |  |  |  |  | 0%
3.3.1 | Brukervennlighet |  |  |  |  | 0%
3.4 | Systemtest |  |  |  |  | 0%
3.4.1 | W3C Validator |  |  |  |  | 0%
4.1 | Ferdigstillelse
4.2 | Lansering av nettside |  |  |  |  | 0%
4.3 | Evaluere lærdom |  |  |  |  | 0%
4.4 | Kontrollere krav |  |  |  |  | 0%